## Worksheet
Education Planning Business Plan (Manager View)
Executive Summary
Project Name: | NextGen Learning Initiative
Purpose: | Education Planning & Skill Development for Future Workforce
Duration: | Q1 2025 – Q4 2027 (3 Years)
Budget: | $1.8M Allocated
Key Objectives & KPIs
Objective | Target Outcome | KPI Metrics | Owner
Increase student enrollment in STEM programs by 30% | 850 new students enrolled by end of Year 2 | Enrollment rate growth, retention rate ≥ 85% | Sarah Chen, Director of Academic Programs
Develop 10 new industry-aligned curricula | Curricula approved and deployed across all campuses | Number of curricula launched, employer feedback score ≥ 4.5/5 | Dr. James Reed, Curriculum Innovation Lead
Improve student job placement rate to 90% | 90% of graduates employed within 6 months of graduation | Placement rate, average starting salary ≥ $58K | Lisa Morgan, Career Services Director
Resource Allocation & Budget Breakdown (USD)
Category | Allocated Amount | Actual Spend (Y1) | % of Total
Faculty & Staff Salaries | $600,000 | $587,234 | 33.3%
Technology & Infrastructure | $450,000 | $421,890 | 25.0%
Curriculum Development | $360,000 | $347,125 | 20.0%
Student Support & Scholarships | $275,000 | $263,489 | 15.3%
Total | $1,685,000 | $1,620,738 | 96.2%
*Remaining budget to be allocated in Q2 2025 based on performance reviews
Timeline & Milestones
Quarter | Milestone | Status | Comments/Notes
Q1 2025 | Finalize strategic partnerships with 5 tech companies | Completed ✅ | Closed agreements with TechNova, DataFlow, and LearnHub Inc.
Q2 2025 | Launch pilot program for AI & Robotics curriculum | In Progress ⏳ | Phase 1: Teacher training completed; student enrollment ongoing.
Q3 2025 | Mid-year performance review and budget realignment | Pending 🗓️ | To be scheduled with Finance & Academic Leads.
Q4 2026 | First cohort of students complete full program and graduate | Planned 🗓️ | Target: 150 graduates; industry job placement event scheduled.
Risk Assessment & Mitigation
Risk Factor | Impact Level | Mitigation Strategy | Status
Faculty turnover in key programs | High ⚠️ | Enhanced retention incentives; internal promotion pipeline established | In Progress ⏳
Market demand for new curricula is lower than expected | Moderate ⚠️ | Conduct quarterly market surveys; flexible curriculum adjustments | Active ✅
Budget overruns due to technology delays | High ⚠️ | Dedicated project manager; monthly budget monitoring dashboard | In Progress ⏳
Prepared by: Education Planning & Strategy Office