## Worksheet
Education Planning Business Plan - Planning View
Executive Summary
Project Name: | [Insert Project Title]
Purpose: | Education Planning
Objective | Target Audience | Timeline (Start - End) | Budget Allocation ($) | Status | Milestones & Deliverables
Develop Curriculum Framework | Students (Grades 9-12), Educators, Parents | Jan 2024 - Jun 2024 | 50,000 | In Progress | Curriculum draft approved by panel; stakeholder feedback integrated.
Recruit Qualified Instructors | Academic Staff, Industry Experts | Mar 2024 - May 2024 | 35,000 | In Progress | Certified educators hired; onboarding complete.
Implement Technology Platform | Students, Faculty, Admin Staff | Apr 2024 - Aug 2024 | 75,000 | Pending Launch | LMS system configured; user training sessions scheduled.
Launch Pilot Program | 12th Grade Cohort (50 Students) | Sep 2024 - Dec 2024 | 60,000 | Pending Launch | Pilot program begins; evaluation metrics established.
Financial Overview (Annual)
Category | Estimated Cost ($) | Actual Spend ($) | Variance ($) | Note: All figures in USD, fiscal year 2024-2025
Curriculum Development | 50,000 | 48,500 | -1,500 (Under Budget)
Instructor Salaries & Benefits | 180,000 | 175,200 | -4,800 (Under Budget)
Technology & Infrastructure | 95,000 | 112,300 | +17,300 (Over Budget) | Delayed software integration caused cost overrun.
Marketing & Outreach | 25,000 | 23,750 | -1,250 (Under Budget)
Key Performance Indicators (KPIs)
KPI | Target | Current Value | Status | Comments / Actions
Student Enrollment Rate | 95% | 92% | On Track | Marketing adjustments in progress to reach target.
Course Completion Rate | 85% | 80% | Slight Delay | Introduce peer mentoring to improve retention.
Stakeholder Satisfaction (Survey) | 4.5/5 | 4.3/5 | Ahead of Target | Positive feedback on curriculum design.
Next Steps & Action Plan
Action Item | Owner | Due Date | Notes / Dependencies
Finalize LMS integration testing | Tech Team Lead | Aug 15, 2024 | Requires access to server environment; third-party vendor support.
Conduct mid-year review of program impact | Program Director | Sep 10, 2024 | Data collected from student surveys and performance records.
Expand outreach to rural communities | Outreach Coordinator | Oct 1, 2024 | Partnership with local NGOs under negotiation.
Note: This is a Planning View template for Education Business Plan purposes. Customize as needed.