## Worksheet
Education Planning Business Plan - Team Use Template
Section | Objective | Key Activities | Responsible Team Member(s) | Status | Dates / Timeline
Executive Summary | Provide a concise overview of the education planning initiative and business goals. | Define mission, vision, target audience, and value proposition. | Team Lead | Pending | 2023-10-01 to 2023-10-15
Market Analysis | Evaluate educational needs, target demographics, and competitive landscape. | Conduct surveys, analyze data, benchmark against competitors. | Research & Insights Team | In Progress | 2023-10-16 to 2023-11-30
Program Development | Design curricula, learning modules, and delivery formats. | Create course outlines, design materials, develop assessment tools. | Curriculum Design Team | Pending | 2023-11-01 to 2024-01-31
Resource Planning | Identify personnel, technology, and financial requirements. | Recruit instructors, acquire software/hardware, budget allocation. | Operations & Finance Team | In Progress | 2023-10-20 to 2023-12-15
Marketing & Outreach | Build awareness and drive enrollment among target audience. | Develop branding, digital campaigns, partner outreach. | Marketing Team | Pending | 2023-12-01 to 2024-03-31
Evaluation & Feedback Loop | Measure success and continuously improve program quality. | Collect feedback, analyze performance metrics, implement improvements. | Evaluation Team | Pending | Ongoing (Starts Q2 2024)
Total Estimated Budget: |  |  |  |  | $1,250,000