## Worksheet
Education Planning - Business Plan - Tracking View
Project Milestone | Description | Target Date | Status | Responsible Person | Budget Allocated ($) | Budget Spent ($)
Needs Assessment Survey | Conduct student and parent survey to identify educational needs | 2023-10-15 | Completed | Jane Smith | 2,500 | 2,350
Curriculum Development Phase 1 | Design core curriculum for grades K-6 based on assessment data | 2023-11-30 | In Progress | Michael Brown | 15,000 | 8,900
Hiring Key Staff Members | Recruit principal, lead teachers, and administrative staff | 2023-12-15 | In Progress | Sarah Johnson | 45,000 | 37,200
Facility Setup and Renovation | Prepare physical space for operation including classroom setup and safety compliance | 2024-01-31 | In Progress | David Lee | 75,000 | 56,800
Digital Learning Platform Integration | Implement LMS and ensure digital infrastructure supports remote learning capabilities | 2024-02-15 | Delayed | Laura Martinez | 30,000 | 18,500
Parent Engagement Program Launch | Begin outreach initiatives and family workshops to build community involvement | 2024-03-10 | Delayed | Tamara White | 8,000 | 3,200
Total Budget (Project) |  |  |  |  | 175,500 | 123,950
Tracking View - Updated as of October 10, 2023. Status colors indicate progress:Completed,In Progress,Delayed