## Worksheet
Advanced Gantt Chart - Education Planning
Task / Activity | Start Date | End Date | Duration (Days) | Progress | Status
Curriculum Design & Approval | 2024-09-01 | 2024-10-31 | 61 |  | In Progress
Faculty Recruitment & Training | 2024-11-01 | 2025-01-31 | 92 |  | Delayed
Student Enrollment Campaign | 2025-01-01 | 2025-03-31 | 90 |  | Planning
Infrastructure Setup & Lab Development | 2024-10-01 | 2025-05-31 | 243 |  | In Progress
Course Material Development | 2024-10-15 | 2025-04-30 | 198 |  | In Progress
Academic Year Launch (Official Opening) | 2025-06-01 | 2025-06-01 | 1 |  | Milestone
Student Orientation & Onboarding | 2025-05-15 | 2025-06-15 | 31 |  | Pending
Mid-Term Evaluation & Curriculum Review | 2025-10-01 | 2025-11-30 | 61 |  | Not Started