## Worksheet
Education Planning - Gantt Chart (Analysis View)
Task | Start Date | End Date | Durations (Days) | Progress
Phase 1: Needs Assessment | 2024-01-05 | 2024-01-30 | 26
1.1 Student Profile Analysis | 2024-01-05 | 2024-01-15 | 10
1.2 Curriculum Gap Identification | 2024-01-16 | 2024-01-30 | 15
Phase 2: Planning & Strategy | 2024-01-31 | 2024-03-15 | 45
2.1 Educational Goals Setting | 2024-01-31 | 2024-02-15 | 15
2.2 Course Selection & Pathway Design | 2024-02-16 | 2024-03-15 | 30
Phase 3: Implementation Preparation | 2024-03-16 | 2024-05-10 | 56
3.1 Enrollment & Documentation | 2024-03-16 | 2024-04-15 | 30
3.2 Visa & Travel Arrangements | 2024-04-16 | 2024-05-10 | 25
Phase 4: Onboarding & Launch | 2024-05-11 | 2024-06-30 | 51
4.1 Orientation Program | 2024-05-11 | 2024-05-31 | 21
4.2 Course Enrollment & Schedule Finalization | 2024-06-01 | 2024-06-30 | 30
Milestone: Academic Year Start | 2024-07-01 | 2024-07-01 | 1