## Education Planning Gantt Chart
Education Planning Gantt Chart
Task | Start Date | End Date | Status | Duration (Days)
Preliminary Research & Goal Setting | 2024-01-01 | 2024-01-15 | In Progress | 15
Course Selection & Enrollment Planning | 2024-01-16 | 2024-01-31 | To Do | 16
Application Preparation (Essays, Transcripts) | 2024-02-01 | 2024-03-15 | To Do | 45
Milestone: Application Submission Deadline | 2024-03-15 | 2024-03-15 | Not Started | 1
Scholarship & Financial Aid Applications | 2024-03-16 | 2024-05-31 | To Do | 77
Interview Preparation & Practice | 2024-06-01 | 2024-06-30 | To Do | 30
Milestone: Acceptance Notification Period Ends | 2024-07-15 | 2024-07-15 | Not Started | 1
School Selection & Enrollment Confirmation | 2024-07-16 | 2024-08-31 | To Do | 47
Housing & Logistics Arrangement | 2024-09-01 | 2024-10-31 | To Do | 61