## Worksheet
Education Planning - Gantt Chart (Client View)
Task | Start Date | End Date | Duration (Days) | Status
Curriculum Development | 2024-03-01 | 2024-05-15 | 76
Faculty Recruitment | 2024-03-10 | 2024-06-30 | 113
Infrastructure Setup | 2024-04-01 | 2024-10-15 | 198
Student Enrollment Campaign | 2024-07-01 | 2024-09-30 | 92
Academic Year Launch | 2024-10-01 | 2024-10-31 | 31 | Complete (Milestone)
Curriculum Review & Updates | 2025-01-01 | 2025-03-15 | 76
Annual Assessment | 2025-06-01 | 2025-06-30 | 31 | Upcoming (Milestone)