## Worksheet
Education Planning - Gantt Chart (Data Version)
Task ID | Task Description | Start Date | End Date | Status | % Complete
1.01 | Curriculum Development | 2024-03-01 | 2024-05-31 | In Progress | 75%
1.02 | Faculty Recruitment | 2024-04-15 | 2024-06-30 | In Progress | 65%
1.03 | Infrastructure Preparation | 2024-03-15 | 2024-07-15 | In Progress | 80%
M1 | Academic Year Kickoff | 2024-08-15 | 2024-08-15 | Milestone Reached | 100%
2.01 | Student Enrollment Campaign | 2024-06-01 | 2024-09-30 | In Progress | 55%
2.02 | Course Delivery - Term 1 | 2024-08-19 | 2025-01-17 | Pending | 0%
2.03 | Midterm Assessments | 2024-10-15 | 2024-10-31 | Pending | 0%
M2 | Midterm Review & Feedback Session | 2024-11-15 | 2024-11-15 | Milestone Pending | 0%
3.01 | Course Delivery - Term 2 | 2025-01-20 | 2025-06-13 | Pending | 0%
M3 | Graduation & Final Exams | 2025-06-13 | 2025-06-13 | Pending | 0%
4.01 | Alumni Engagement & Feedback Collection | 2025-06-15 | 2025-08-31 | Pending | 0%
M4 | Program Evaluation & Review | 2025-09-30 | 2025-09-30 | Pending | 0%
Note: This Gantt chart represents a data version of the Education Planning template. Dates and statuses are illustrative.