## Worksheet
Education Planning - Detailed Gantt Chart
Task ID | Task Name | Description | Start Date | End Date | Duration (Days) | Status | Progress (%)
E101 | Academic Goals Definition | Define short and long-term academic objectives for student. | 2024-09-01 | 2024-09-15 | 15 | In Progress
E102 | Curriculum & Course Selection | Select appropriate academic courses based on goals and prerequisites. | 2024-09-16 | 2024-10-31 | 46 | In Progress
E103 | Standardized Test Prep (SAT/ACT) | Enroll in prep courses, schedule test dates. | 2024-10-01 | 2025-01-31 | 123 | Pending
E104 | College Research and Selection | Analyze academic programs, location, cost, and admission stats. | 2024-11-01 | 2025-03-31 | 152 | Pending
E105 | Personal Statement and Essay Writing | Develop compelling narratives for college applications. | 2025-01-01 | 2025-04-30 | 121 | Pending
E106 | College Application Submission | Submit applications to target schools with all required documents. | 2025-04-01 | 2025-11-30 | 244 | Pending
E107 | Scholarship Research and Application | Apply for merit, need-based, and external scholarships. | 2025-03-01 | 2025-11-30 | 274 | Pending
E108 | Complete FAFSA & Financial Aid Forms | Submit required financial documentation and aid applications. | 2025-01-01 | 2025-06-30 | 181 | Pending
M101 | Final College Acceptance Decision | Review all offers, compare financial packages, and make final decision. | 2025-06-30 | 2025-07-31 | 31 | Milestone Achieved
E109 | Enrollment Confirmation and Orientation | Confirm attendance, attend orientation sessions, register for classes. | 2025-08-01 | 2025-08-31 | 31 | Pending