## Worksheet
Task ID | Task Name | Start Date | End Date | Durations (Days) | Status | Progress (%)
1 | Phase 1: Planning & Setup
1.1 | Define Educational Objectives | 2025-04-01 | 2025-04-07 | 7 | In Progress
1.2 | Identify Target Curriculum Areas | 2025-04-08 | 2025-04-15 | 8 | In Progress
1.3 | Develop Learning Outcomes Framework | 2025-04-16 | 2025-04-23 | 8 | Pending
2 | Phase 2: Resource Allocation
2.1 | Assign Subject Specialists | 2025-04-24 | 2025-05-03 | 10 | Pending
2.2 | Secure Educational Materials & Tools | 2025-05-04 | 2025-05-11 | 8 | Pending
2.3 | Establish Learning Platforms & LMS Setup | 2025-05-12 | 2025-05-18 | 7 | Pending
3 | Phase 3: Curriculum Development
3.1 | Create Detailed Module Syllabi | 2025-05-19 | 2025-06-16 | 28 | Pending
3.2 | Develop Lesson Plans and Activities | 2025-06-17 | 2025-07-14 | 28 | Pending
3.3 | Review and Finalize Curriculum Draft | 2025-07-15 | 2025-07-21 | 7 | Pending
4 | Phase 4: Pilot & Feedback
4.1 | Conduct Pilot Program (Small Group) | 2025-07-22 | 2025-08-19 | 38 | Pending
4.2 | Collect Feedback from Participants & Educators | 2025-08-15 | 2025-08-31 | 17 | Pending
4.3 | Implement Revisions Based on Feedback | 2025-09-01 | 2025-09-14 | 14 | Pending
5 | Phase 5: Final Implementation
5.1 | Roll Out Curriculum Across All Programs | 2025-09-15 | 2026-03-31 | 230 | Pending
M1 | Curriculum Approval – Final Sign-Off | 2025-07-21 | 2025-07-21 | 1 | Milestone Achieved
M2 | Full Educational Program Launch | 2026-04-01 | 2026-04-01 | 1 | Milestone Pending
Total Duration (Days) |  |  |  | 316 | Overall Progress