## Worksheet
Education Planning Gantt Chart - Financial View
Task / Milestone | Start Date | End Date | Duration (Months) | Budget Allocated ($) | Progress (%)
Curriculum Development | Jan 2024 | Mar 2024 | 3 | 15,000
Faculty Hiring | Feb 2024 | Apr 2024 | 3 | 45,000
Infrastructure Upgrade | Mar 2024 | Jul 2024 | 5 | 110,000
Program Launch (Milestone) | Aug 2024 | Aug 2024 | 1 | 5,000
Student Recruitment | Jun 2024 | Sep 2024 | 4 | 30,000
Technology Integration | Jul 2024 | Nov 2024 | 5 | 85,000
First Semester Start (Milestone) | Aug 2024 | Aug 2024 | 1 | 3,500
Financial Aid Distribution | Aug 2024 | Sep 2024 | 1 | 75,000
Academic Review & Evaluation | Dec 2024 | Jan 2025 | 2 | 18,000
Total | - |  |  | $441,500 | -
* Financial View Gantt Chart - Education Planning Template ¦ Data as of October 2023