## Worksheet
Education Planning Gantt Chart - Large Business Style
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
P1.01 | Project Charter Development | 2024-01-05 | 2024-01-15 | 10 | In Progress
P1.02 | Stakeholder Identification & Engagement | 2024-01-16 | 2024-01-30 | 15 | In Progress
P1.03 | Resource Allocation Plan | 2024-01-31 | 2024-02-15 | 16 | Milestone - Planning Complete
Academic Curriculum Development Phase
P2.01 | Curriculum Framework Design | 2024-02-16 | 2024-03-15 | 30 | In Progress
P2.02 | Course Syllabus Development | 2024-03-16 | 2024-04-30 | 45 | In Progress
Faculty & Training Phase
P3.01 | Faculty Recruitment & Hiring | 2024-05-01 | 2024-06-15 | 45 | In Progress
P3.02 | Faculty Onboarding & Training | 2024-06-16 | 2024-07-31 | 46 | In Progress
Infrastructure & Technology Phase
P4.01 | Learning Management System (LMS) Setup | 2024-08-01 | 2024-09-30 | 61 | In Progress
P4.02 | Classroom & Lab Facility Construction | 2024-08-15 | 2025-01-31 | 169 | In Progress
Student Enrollment & Launch Phase
P5.01 | Admission Campaign & Marketing | 2025-02-01 | 2025-04-30 | 91 | Scheduled
P5.02 | Student Enrollment & Registration | 2025-04-31 | 2025-07-31 | 93 | Scheduled
P5.03 | Academic Year Kickoff & Launch | 2025-08-15 | 2025-08-15 | 1 | Milestone - Launch Date
Total Duration |  |  |  | 527 days | Project Completion: 2025-08-15