## Worksheet
Education Planning - Gantt Chart (Manager View)
Task | Start Date | End Date | Duration (Days) | Status | Progress
Phase 1: Planning & Strategy (Q1)
Needs Assessment | 2024-01-05 | 2024-01-19 | 15 | In Progress
Curriculum Design Workshop | 2024-01-22 | 2024-01-31 | 10 | In Progress
Phase 2: Resource Development (Q2)
Learning Materials Creation | 2024-02-01 | 2024-03-15 | 45 | Not Started
E-Learning Platform Setup | 2024-02-15 | 2024-03-31 | 45 | Not Started
Phase 3: Pilot Implementation (Q3)
Pilot Launch - Grade 9 | 2024-04-01 | 2024-06-30 | 91 | Not Started
Phase 4: Evaluation & Expansion (Q4)
Post-Pilot Review | 2024-07-01 | 2024-07-31 | 31 | Not Started
Full Implementation - All Grades | 2024-08-15 | 2024-11-30 | 108 | Not Started
Milestones
Curriculum Finalized | 2024-01-31 |  |  | Completed
Pilot Launch Complete | 2024-06-30 |  |  | Not Started
Final Evaluation Report | 2024-08-15 |  |  | Not Started
Last updated: October 5, 2023 ¦ Manager View - Education Planning Gantt Chart