## Worksheet
Education Planning - Gantt Chart (Planning View)
Task | Start Date | End Date | Duration (Days) | Status
Academic Year Planning | 2024-09-01 | 2025-06-30 | 273
Course Selection & Enrollment | 2024-09-15 | 2024-11-30 | 76
Entrance Exam Preparation | 2024-10-01 | 2025-03-31 | 182
University Applications | 2025-01-01 | 2025-04-30 | 120
Financial Aid Applications | 2025-01-15 | 2025-06-15 | 153
Acceptance & Enrollment Confirmation | 2025-05-01 | 2025-07-31 | 91
Housing & Travel Arrangements | 2025-06-15 | 2025-08-15 | 61
Pre-Departure Orientation | 2025-08-15 | 2025-08-17 | 3 | Completed
Final Academic & Personal Prep | 2025-08-18 | 2025-08-31 | 14
Departure & Arrival | 2025-09-01 | 2025-09-03 | 3 | Scheduled
First Semester (Academic Start) | 2025-09-04 | 2026-01-31 | 149
Mid-Term Academic Review | 2025-11-03 | 2025-11-07 | 5 | Completed
End of First Semester | 2026-01-31 | 2026-01-31 | 0 | Scheduled
Note:This Gantt chart is a planning view for education preparation. Progress bars indicate approximate completion status. Milestones are highlighted in red.