## Worksheet
Education Planning Gantt Chart - Small Business
Task | Start Date | End Date | Duration (Days) | Status
Needs Assessment & Goal Setting | 2024-01-05 | 2024-01-15 | 11
Curriculum Development | 2024-01-16 | 2024-03-15 | 60
Resource Acquisition | 2024-01-16 | 2024-02-15 | 30
Staff Training & Onboarding | 2024-02-16 | 2024-03-15 | 30
Student Enrollment & Registration | 2024-03-16 | 2024-04-15 | 31
Course Launch & Orientation | 2024-04-16 | 2024-04-30 | 15
Mid-Term Evaluation | 2024-05-15 | 2024-05-31 | 17
Final Assessment & Certification | 2024-06-10 | 2024-06-30 | 21
Program Completion & Review (Milestone)
Project Duration:Jan 5, 2024 – Jun 30, 2024 (Total: 198 days)