## Worksheet
Education Planning Gantt Chart - Startup Style
Task / Milestone | Start Date | End Date | Status | Progress
Phase 1: Planning & Research | Jan 05, 2024 | Jan 30, 2024 | Completed
Define Learning Goals | Jan 05, 2024 | Jan 10, 2024 | Completed
Research Curriculum Options | Jan 11, 2024 | Jan 20, 2024 | Completed
Select Learning Platform | Jan 21, 2024 | Jan 30, 2024 | Completed
Phase 2: Course Enrollment | Feb 01, 2024 | Feb 15, 2024 | In Progress
Apply to Programs | Feb 01, 2024 | Feb 07, 2024 | In Progress
Secure Funding & Scholarships | Feb 08, 2024 | Feb 15, 2024 | In Progress
Milestone: Enrollment Confirmation | Feb 15, 2024 | Feb 15, 2024 | Upcoming
Phase 3: Preparation | Feb 16, 2024 | Mar 10, 2024 | Not Started
Finalize Schedule | Feb 16, 2024 | Feb 25, 2024 | Not Started
Gather Materials | Feb 26, 2024 | Mar 05, 2024 | Not Started
Pre-Program Orientation | Mar 06, 2024 | Mar 10, 2024 | Not Started
Phase 4: Execution | Mar 11, 2024 | Jun 30, 2024 | Not Started
Begin Course Work | Mar 11, 2024 | Apr 30, 2024 | Not Started
Mid-Term Review | May 01, 2024 | May 15, 2024 | Not Started
Final Project & Submission | Jun 16, 2024 | Jun 30, 2024 | Not Started
Milestone: Completion Certificate | Jul 05, 2024 | Jul 05, 2024 | Not Started