## Worksheet
Education Planning - Gantt Chart (Summary View)
Phase / Task | Start Date | End Date | Status | Duration (Weeks)
Phase 1: Needs Assessment | 2024-09-01 | 2024-09-30 | In Progress | 4 weeks
• Conduct Student Surveys | 2024-09-01 | 2024-09-15 | In Progress | 2 weeks
• Analyze Academic Data | 2024-09-16 | 2024-09-30 | In Progress | 2 weeks
Phase 2: Curriculum Development | 2024-10-01 | 2024-11-30 | Pending | 8 weeks
• Draft Course Syllabi | 2024-10-01 | 2024-10-31 | Pending | 4 weeks
• Review and Approve Curriculum | 2024-11-01 | 2024-11-30 | Pending | 4 weeks
Phase 3: Resource Planning | 2024-12-01 | 2025-01-15 | Pending | 7 weeks
• Budget Allocation & Procurement | 2024-12-01 | 2024-12-31 | Pending | 4 weeks
• Faculty Recruitment & Training | 2025-01-01 | 2025-01-15 | Pending | 3 weeks
Phase 4: Implementation | 2025-01-16 | 2025-06-30 | Pending | 24 weeks
• Rollout Pilot Program | 2025-01-16 | 2025-03-31 | Pending | 10 weeks
• Full Program Launch | 2025-04-01 | 2025-06-30 | Pending | 13 weeks
• Final Review & Approval (Milestone) | 2025-06-30 | 2025-06-30 | Not Started | 1 day
Note:This Gantt chart summary view provides a high-level overview of the education planning timeline. Actual dates and status may vary.