## Worksheet
Education Planning Gantt Chart - Team Use
Task / Milestone | Team Member(s) | Start Date | End Date | Status
Project Kickoff & Requirements Gathering | Team A, Team B | 2025-01-06 | 2025-01-17 | 95%
Curriculum Development & Review | Team C, Team D | 2025-01-18 | 2025-02-14 | 65%
LMS Integration & Content Setup | Team E, Team F | 2025-02-17 | 2025-03-14 | 35%
User Acceptance Testing (UAT) | Team A, Team G | 2025-03-17 | 2025-03-31 | 15%
Final Review & Approval | Project Lead, Academic Board | 2025-04-03 | 2025-04-11 | 0%
Training & Onboarding (Staff) | Team H, Team I | 2025-04-14 | 2025-04-30 | 5%
First Semester Pilot Launch | All Teams | 2025-05-01 | 2025-06-30 | 1%
Note: This Gantt chart is designed for team collaboration in education planning. All dates are subject to change based on feedback and review cycles.