## Worksheet
Task | Responsible Team Member | Due Date | Status | Progress (%)
Create Course Curriculum Outline | Academic Planning Team | 2024-04-15 | In Progress | 65
Secure Instructor Assignments | HR & Academic Coordination | 2024-04-20 | Pending Approval | 30
Schedule Classroom Availability | Facilities Management | 2024-04-18 | Completed | 100
Develop Student Enrollment Materials | Marketing & Admissions | 2024-04-25 | In Progress | 70
Evaluate Program Outcomes Metrics | Educational Research Team | 2024-05-10 | Not Started | 0
Conduct Final Review Meeting | All Stakeholders (Team) | 2024-05-15 | Not Started | 0