## Worksheet
Education Planning - Project Plan
Analysis View ¦ Template Type: Project Plan ¦ Purpose: Education Planning
Phase/Task | Owner | Start Date | End Date | Status | Budget (USD) | % Complete
Needs Assessment & Requirements Gathering | Dr. Sarah Johnson | 2024-01-15 | 2024-01-31 | In Progress | $7,500.00 | 65%
Curriculum Design & Development | Prof. Michael Chen | 2024-02-01 | 2024-03-15 | In Progress | $35,000.00 | 48%
Faculty Recruitment & Training | Lisa Rodriguez, HR Lead | 2024-02-15 | 2024-03-31 | In Progress | $58,750.00 | 37%
Infrastructure & Facility Setup | David Kim, Facilities Mgr. | 2024-01-20 | 2024-05-31 | In Progress | $156,800.00 | 73%
Student Recruitment & Enrollment | Amy Patel, Admissions Director | 2024-03-15 | 2024-06-15 | In Progress | $8,950.00 | 14%
Technology Integration & LMS Setup | James Wilson, IT Director | 2024-02-10 | 2024-04-30 | In Progress | $45,500.00 | 68%
External Accreditation & Compliance Review | Sarah Thompson, Compliance Officer | 2024-03-31 | 2024-05-15 | Delayed (Pending) | $18,600.00 | 9%
Total |  |  |  | Overall Progress: 43% | $321,150.00