## Worksheet
Annual Education Planning Project Plan
Project Phase | Activity Description | Responsible Team/Person | Start Date | End Date | Status | Budget Allocated (USD)
Planning & Needs Assessment | Conduct curriculum gap analysis and stakeholder consultations. | Academic Planning Committee | 2024-01-01 | 2024-03-31 | In Progress | $5,000
Curriculum Development | Design and draft new course modules and learning materials. | Instructional Design Team | 2024-04-01 | 2024-06-30 | Pending | $35,000
Faculty Training | Organize professional development sessions for teaching staff. | HR & Training Department | 2024-07-15 | 2024-08-31 | Pending | $15,000
Implementation Phase I | Roll out new curriculum in pilot departments. | Department Heads & Instructors | 2024-09-15 | 2024-11-30 | Pending | $25,000
Evaluation & Feedback Collection | Gather student and faculty feedback for improvement. | Academic Assessment Office | 2024-12-01 | 2024-12-31 | Pending | $8,000
Total Project Budget: | [5 empty] | $93,000
Notes:
All dates are in YYYY-MM-DD format.
Status: Pending / In Progress / Completed.
Budget allocated reflects estimated costs per phase.