## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
T001 | Define project objectives and scope | Project Manager | 2023-10-01 | 2023-10-05 | To Do
T002 | Identify target students and needs assessment | Education Specialist | 2023-10-06 | 2023-10-15 | In Progress
T003 | Develop curriculum outline | Curriculum Designer | 2023-10-16 | 2023-10-25 | In Progress
T004 | Secure teaching resources and materials | Resource Coordinator | 2023-10-26 | 2023-11-05 | To Do
T005 | Recruit and train teaching staff | Hiring Manager | 2023-11-06 | 2023-11-15 | To Do
T006 | Conduct pilot program with selected students | Project Manager | 2023-11-16 | 2023-11-30 | To Do
T007 | Evaluate pilot results and adjust curriculum | Education Specialist | 2023-12-01 | 2023-12-10 | To Do
T008 | Full-scale project launch and monitoring | Project Manager | 2023-12-11 | 2024-03-31 | To Do