## Worksheet
Education Planning - Project Plan
Task ID | Task Name | Description | Responsible Person | Status | Start Date | End Date
T001 | Needs Assessment | Evaluate current educational resources and student requirements. | Dr. Amanda Lee | Completed | 2024-03-15 | 2024-03-31
T002 | Curriculum Development | Design updated course syllabi and learning modules. | Prof. James Carter | In Progress | 2024-04-01 | 2024-06-15
T003 | Faculty Training | Organize workshops for teachers on new curriculum delivery. | Sarah Williams | Not Started | 2024-06-16 | 2024-07-31
T004 | Resource Procurement | Purchase textbooks, lab equipment, and digital tools. | Robert Green | Not Started | 2024-07-15 | 2024-08-30
T005 | Implementation Phase | Roll out new curriculum across departments. | Lisa Thompson | Not Started | 2024-09-15 | 2024-11-30
T006 | Evaluation & Feedback | Collect feedback and assess program outcomes. | Maria Gonzalez | Not Started | 2024-12-01 | 2025-01-31