## Worksheet
Education Planning - Project Plan (Client View)
Phase | Task Description | Start Date | End Date | Status | Responsible Party | Budget Allocation (USD)
1. Needs Assessment | Conduct initial student and program needs analysis | 2023-10-01 | 2023-10-15 | Pending | Sarah Johnson (Consultant) | $8,500.00
2. Curriculum Development | Design and align curriculum with learning objectives | 2023-10-16 | 2023-11-30 | In Progress | Alex Rivera (Lead Educator) | $45,000.00
3. Resource Acquisition | Procure learning materials, technology, and tools | 2023-12-01 | 2024-01-15 | Not Started | Jamal Thompson (Procurement) | $68,750.00
4. Faculty Training | Train teaching staff on new curriculum delivery methods | 2024-01-16 | 2024-02-15 | Not Started | Linda Chen (Training Coordinator) | $36,900.00
5. Pilot Program Launch | Implement program with selected cohort for testing | 2024-02-16 | 2024-04-30 | Not Started | Maria Gonzalez (Project Director) | $75,300.00
6. Evaluation & Refinement | Analyze pilot results and refine program components | 2024-05-01 | 2024-06-15 | Not Started | Sarah Johnson (Consultant) | $38,450.00
7. Full Implementation | Roll out program across all target institutions | 2024-06-16 | 2025-10-31 | Not Started | Maria Gonzalez (Project Director) | $385,750.00
Project End Date: October 31, 2025