## Worksheet
Task ID | Task Name | Responsible | Start Date | End Date | Status
T001 | Define Project Scope | Jane Doe | 2024-04-01 | 2024-04-05 | In Progress
T002 | Develop Curriculum Outline | Jane Doe, Mark Lee | 2024-04-15 | 2024-05-15 | Pending
T003 | Secure Funding Approval | Emily Clark | 2024-04-18 | 2024-05-15 | In Progress
T004 | Hire Teaching Staff | Emily Clark, Mark Lee | 2024-05-16 | 2024-06-30 | Pending
T005 | Procure Learning Materials | Daniel Kim | 2024-05-18 | 2024-06-15 | In Progress
T006 | Student Recruitment Campaign | Daniel Kim, Jane Doe | 2024-06-15 | 2024-07-31 | Pending
T007 | Finalize Program Timeline | Mark Lee | 2024-06-15 | 2024-07-15 | Pending
T008 | Launch Program Pilot Phase | All Team Members | 2024-08-15 | 2024-11-30 | Pending