## Worksheet
Education Planning Project Dashboard
Project Plan ¦ Status: In Progress ¦ Last Updated: April 5, 2024
Task ID | Task Name | Responsible Team | Start Date | Due Date | Status | Progress (%)
P001 | Curriculum Development Phase 1 | Academic Department | 2024-03-15 | 2024-04-30 | In Progress
P002 | Faculty Recruitment | HR & Academic | 2024-03-18 | 2024-05-15 | In Progress
P003 | Infrastructure Upgrades | Facilities Team | 2024-03-25 | 2024-06-15 | Pending
P004 | Student Enrollment Campaign | Marketing & Admissions | 2024-04-15 | 2024-07-31 | Pending
P005 | Technology Integration | IT Department | 2024-03-10 | 2024-05-31 | Completed
P006 | Program Evaluation Framework | Academic Review Board | 2024-04-10 | 2024-05-31 | In Progress