## Worksheet
Phase | Activity/Task | Description | Responsible Party | Start Date | End Date | Status
Planning Phase | Needs Assessment Survey | Conduct survey to identify educational needs and goals of target students. | Academic Coordinator | 2025-04-01 | 2025-04-10 | In Progress
| Curriculum Design Workshop | Host workshop with educators to design course outlines and learning objectives. | Curriculum Team Lead | 2025-04-11 | 2025-04-15 | Pending
| Budget Allocation Review | Analyze funding sources and allocate budget per program component. | Finance Officer | 2025-04-16 | 2025-04-18 | Pending
Implementation Phase | Course Development | Create detailed lesson plans, materials, and assessments. | Instructional Designer | 2025-04-19 | 2025-05-10 | Pending
| Instructor Training Session | Train educators on new curriculum delivery methods and tools. | Training Coordinator | 2025-05-11 | 2025-05-14 | Pending
| Program Launch Event | Organize and host official launch for students, parents, and staff. | Project Manager | 2025-05-15 | 2025-05-17 | Pending
Monitoring & Evaluation Phase | Mid-Term Progress Review | Evaluate student performance and program effectiveness after 8 weeks. | Program Evaluator | 2025-05-18 | 2025-05-31 | Pending
| Feedback Collection (Students & Teachers) | Gather qualitative feedback through surveys and focus groups. | Research Assistant | 2025-06-01 | 2025-06-14 | Pending
| Final Report Preparation | Draft comprehensive report summarizing outcomes, challenges, and recommendations. | Project Manager & Analysts | 2025-06-15 | 2025-06-30 | Pending
Notes:
Status options: Not Started, Pending, In Progress, Completed.
Project Duration: April 1, 2025 – June 30, 2025.
This plan is subject to change based on feedback and resource availability.