## Worksheet
Education Planning Project Plan - Extended Template
Phase / Task | Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
Phase 1: Needs Assessment
Conduct Stakeholder Interviews | Engage with students, parents, faculty, and administration to gather insights on educational goals and challenges. | Project Manager & Team Lead | 2024-01-05 | 2024-01-19 | In Progress | $3,500
Review Current Curriculum Frameworks | Analyze existing curricula across subjects and grade levels to identify gaps and redundancies. | Academic Director & Curriculum Specialist | 2024-01-15 | 2024-01-31 | Not Started | $5,000
Phase 2: Goal Setting & Strategy Development
Define Long-Term Educational Objectives | Establish measurable, time-bound goals aligned with institutional vision and student success indicators. | Strategic Planning Committee | 2024-02-01 | 2024-02-15 | Not Started | $7,500
Develop Implementation Roadmap | Create a phased timeline with key milestones, deliverables, and dependencies. | Project Manager & Planning Team | 2024-02-10 | 2024-03-15 | Not Started | $6,800
Phase 3: Curriculum & Resource Planning
Design New Course Modules | Develop innovative, interdisciplinary course content focused on critical thinking and digital literacy. | Subject Matter Experts & Instructional Designers | 2024-03-16 | 2024-05-31 | Not Started | $45,000
Procure Learning Materials & Technology Tools | Identify and purchase required textbooks, software licenses, and digital learning platforms. | Purchasing Officer & IT Coordinator | 2024-04-01 | 2024-06-30 | Not Started | $75,500
Phase 4: Pilot Implementation
Run Pilot Program (Grade 9 & 10) | Launch selected modules in two pilot classes with real-time monitoring and feedback collection. | Lead Teachers & Instructional Coaches | 2024-07-01 | 2024-11-30 | Not Started | $38,500
Phase 5: Evaluation & Scaling
Collect and Analyze Pilot Data | Evaluate student performance, teacher feedback, and engagement metrics from pilot phase. | Research Analysts & Academic Review Board | 2024-11-01 | 2025-01-31 | Not Started | $28,750
Refine Curriculum Based on Feedback | Merge insights from evaluation into final curriculum adjustments and training materials. | Curriculum Team & Training Coordinators | 2025-01-15 | 2025-03-31 | Not Started | $42,300
Phase 6: Full Rollout & Training
Implement Across All Grades | Roll out updated curriculum to all grade levels with phased integration. | All Department Heads & Teachers | 2025-04-01 | 2026-06-30 | Not Started | $157,800
Total Project Budget (Estimated) | $439,250 | [5 empty] | $439,250
Note:This project plan template is designed for educational institutions aiming to modernize and enhance their academic offerings. All dates are subject to change based on resource availability, stakeholder feedback, and external factors.