## Worksheet
Education Planning - Financial View Project Plan
Project Phase | Task Description | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Status | % Complete
Phase 1: Planning | Define education goals and objectives | 2024-01-05 | 2024-01-15 | 5,000 | 4,850 | In Progress | 97%
| Identify funding sources and scholarships | 2024-01-16 | 2024-01-31 | 3,500 | 3,350 | In Progress | 96%
| Create detailed timeline and milestones | 2024-02-01 | 2024-02-15 | 1,500 | 1,485 | Pending Approval | 99%
Phase 2: Application Preparation | Prepare academic transcripts and records | 2024-02-16 | 2024-03-15 | 8,000 | 7,950 | In Progress | 99%
| Gather recommendation letters and support documents | 2024-03-16 | 2024-04-15 | 6,500 | 6,485 | In Progress | 99%
| Complete university application forms and essays | 2024-04-16 | 2024-05-31 | 7,500 | 7,498 | Pending Submission | 99%
Phase 3: Evaluation & Acceptance | Track application status and follow-up | 2024-06-01 | 2024-07-31 | 5,000 | 4,975 | In Progress | 99%
| Analyze acceptance offers and financial aid packages | 2024-08-01 | 2024-08-31 | 3,500 | 3,495 | Pending Decision | 99%
Phase 4: Finalization | Select institution and confirm enrollment | 2024-09-01 | 2024-09-15 | 6,800 | 6,785 | Pending Decision | 99%
| Submit enrollment deposit and finalize paperwork | 2024-09-16 | 2024-10-31 | 5,500 | 5,498 | Pending Action | 99%
Total Project Budget: |  |  |  | $52,800 | $51,736 | Overall Progress | 98%
Data updated on: October 26, 2024 ¦ Prepared for Educational Planning Initiative