## Worksheet
Education Planning - Project Plan (Freelancer Style)
Task ID | Task Description | Assigned To | Due Date | Status | Priority | Budget (USD)
TASK-001 | Define project scope and objectives for educational curriculum development | Dr. Alice Johnson | 2024-04-15 | Completed | High | $1,500.00
TASK-002 | Conduct stakeholder needs assessment (teachers, parents, students) | Mark Reynolds | 2024-04-18 | In Progress | High | $950.00
TASK-003 | Design initial course modules for STEM education program | Sarah Chen | 2024-04-25 | In Progress | Medium | $2,100.00
TASK-004 | Develop assessment tools and learning outcomes framework | James Wilson | 2024-05-01 | Pending | High | $1,300.00
TASK-005 | Review and finalize curriculum draft with expert panel | Dr. Alice Johnson | 2024-05-10 | Pending | Medium | $850.00
TASK-006 | Organize pilot program launch for 3 high schools | Mark Reynolds | 2024-05-15 | Pending | High | $3,200.00
TASK-007 | Collect feedback from pilot program and analyze results | Sarah Chen | 2024-06-15 | Pending | Medium | $1,750.00
TASK-008 | Update curriculum based on feedback and prepare full rollout plan | James Wilson | 2024-06-30 | Pending | High | $2,850.00
Total Project Budget: | [5 empty] | $14,500.00