## Worksheet
Education Planning - Project Plan
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete(Progress)
Phase 1: Needs Assessment & Planning
EP-001 | Conduct Stakeholder Interviews (Admin, Faculty, Students) | Planning Committee | 2024-01-15 | 2024-01-31 | In Progress | 65%
EP-002 | Review Existing Curriculum & Learning Outcomes | Academic Council | 2024-01-18 | 2024-02-15 | In Progress | 78%
EP-003 | Develop Needs Assessment Report | Planning Committee | 2024-02-16 | 2024-03-15 | Delayed | 35%
Phase 2: Curriculum Design & Development
EP-004 | Design New Course Frameworks (Core & Electives) | Curriculum Design Team | 2024-03-18 | 2024-05-31 | In Progress | 57%
EP-005 | Create Learning Materials & Digital Resources | Instructional Designers | 2024-04-01 | 2024-06-30 | Completed | 100%
Phase 3: Implementation & Review
EP-006 | Train Faculty on New Curriculum | Faculty Development Office | 2024-07-15 | 2024-08-31 | Delayed | 15%
EP-007 | Launch Pilot Program (Year 1) | Academic Council & Admin | 2024-09-01 | 2025-12-31 | Completed | 88%
EP-008 | Collect Feedback & Finalize Curriculum | Evaluation Team | 2025-01-15 | 2025-03-31 | Completed | 96%
Project Summary
Overall Project Completion: | [5 empty] | 79%
Prepared by: Education Planning Office ¦ Last Updated: April 5, 2024