## Worksheet
Education Planning - Project Plan
Project Title:Educational Development Initiative 2024
Date Prepared:April 5, 2024
Phase | Task Description | Start Date | End Date | Responsible Party | Status
Phase 1: Needs Assessment & Planning
Phase 1 | Conduct stakeholder interviews and surveys | 2024-04-08 | 2024-04-15 | Project Manager, Dr. Jane Smith | In Progress
Phase 1 | Analyze educational gaps and requirements | 2024-04-16 | 2024-04-25 | Data Analyst Team, Ms. Lisa Chen | Pending
Phase 2: Curriculum Development
Phase 2 | Design core curriculum framework for primary level | 2024-04-26 | 2024-05-15 | Curriculum Design Team, Mr. Robert Johnson | Pending
Phase 2 | Develop supplementary materials and digital resources | 2024-05-16 | 2024-06-10 | Digital Content Team, Ms. Ava Patel | Pending
Phase 3: Pilot Implementation & Evaluation
Phase 3 | Deploy curriculum in three pilot schools (Q2) | 2024-06-11 | 2024-08-31 | Pilot Coordinator, Dr. Elena Rodriguez | Pending
Phase 3 | Collect feedback and assess student performance metrics | 2024-09-01 | 2024-09-30 | Evaluation Team, Mr. Tom Wilson | Pending
Phase 4: Full Rollout & Monitoring
Phase 4 | Scale implementation to all participating schools (Q4) | 2024-10-01 | 2025-01-31 | School Implementation Lead, Ms. Grace Lee | Pending
Phase 4 | Establish ongoing monitoring and improvement system | 2025-02-01 | 2025-12-31 | M&E Specialist, Dr. Marcus Brown | Pending
© 2024 Education Planning Division. All rights reserved.