## Worksheet
Education Planning - Project Plan - Planning View
Phase / Activity | Start Date | End Date | Responsible Team/Person | Status | Progress (%)
Phase 1: Needs Assessment & Planning
Conduct stakeholder consultation sessions | 2024-03-01 | 2024-03-15 | Planning Committee, Admin Team | In Progress | 75%
Analyze current educational infrastructure | 2024-03-10 | 2024-03-31 | Data Analysis Unit, Site Surveyors | In Progress | 65%
Phase 2: Curriculum Development
Define core learning objectives & outcomes | 2024-04-01 | 2024-04-15 | Academic Council, Subject Leads | Delayed (Pending Review) | 35%
Develop subject-specific syllabi | 2024-04-16 | 2024-05-31 | Syllabus Development Team | In Progress | 50%
Phase 3: Resource Allocation & Budgeting
Identify required teaching materials and equipment | 2024-05-01 | 2024-05-15 | Purchasing Office, IT Dept. | Completed | 100%
Finalize annual education budget proposal | 2024-05-16 | 2024-06-15 | Finance & Operations Team | Delayed (Pending Approval) | 70%
Phase 4: Implementation Preparation
Recruit and train teaching staff | 2024-06-01 | 2024-07-31 | Hiring Committee, HR Department | Completed | 100%
Develop student enrollment and onboarding process | 2024-07-01 | 2024-08-31 | Student Services, IT Team | Delayed (System Integration Pending) | 55%
Milestones
Project Kick-off Meeting | 2024-03-01 | 2024-03-01 | Project Manager | Milestone Achieved | 100%
Curriculum Framework Finalized | 2024-05-31 | 2024-05-31 | Academic Council | Milestone Pending Review | 95%
Full Project Plan Approved | 2024-06-15 | 2024-06-15 | Executive Board | Milestone Pending Approval | 98%
Total Tasks |  |  | 14 Team Members | Avg. Progress | 67%