## Education Planning Project Plan
Education Planning Project Plan
Printable Template ¦ Purpose: Education Planning ¦ Template Type: Project Plan
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
TASK-001 | Define project scope and objectives | Project Manager | 2024-01-15 | 2024-01-25 | In Progress | $1,500.00
TASK-002 | Conduct needs assessment survey | Research Coordinator | 2024-01-26 | 2024-02-15 | Not Started | $3,000.00
TASK-003 | Develop curriculum framework | Curriculum Designer | 2024-02-16 | 2024-03-15 | Not Started | $5,500.00
TASK-004 | Recruit teaching staff | Hiring Manager | 2024-03-16 | 2024-04-15 | Not Started | $8,000.00
TASK-005 | Procure learning materials and equipment | Purchasing Officer | 2024-04-16 | 2024-05-15 | Not Started | $15,000.00
TASK-006 | Launch pilot program | Project Manager | 2024-05-16 | 2024-07-31 | Not Started | $7,500.00
TASK-007 | Evaluate pilot outcomes and adjust plan | Program Analyst | 2024-08-15 | 2024-09-30 | Not Started | $6,500.00
Total Budget: | [5 empty] | $57,000.00