## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
EP-001 | Needs Assessment & Goal Setting | Dr. Sarah Johnson | 2024-01-15 | 2024-01-31 | In Progress | $3,500
EP-002 | Curriculum Development Phase 1 | Prof. Michael Chen | 2024-02-01 | 2024-03-15 | Pending | $8,750
EP-003 | Resource Procurement & Vendor Contracts | Linda Patel, Admin Manager | 2024-02-15 | 2024-03-10 | Pending | $6,900
EP-004 | Faculty Recruitment & Onboarding | HR Department - Emma Reed | 2024-03-15 | 2024-05-31 | Pending | $15,800
EP-005 | Student Enrollment & Admission Process | Admissions Office - James Wright | 2024-04-15 | 2024-06-30 | Pending | $7,500
EP-006 | Infrastructure & Facility Readiness Check | Facility Management - David Kim | 2024-05-15 | 2024-07-31 | Pending | $9,600
EP-007 | Final Review & Approval by Academic Board | Dean of Academics - Dr. Anna Turner | 2024-08-15 | 2024-09-15 | Pending | $4,300
EP-008 | Launch & Orientation Program for Students & Staff | Project Lead - Lisa Morgan | 2024-10-01 | 2024-11-30 | Pending | $5,750