## Worksheet
Education Planning - Quarterly Project Plan
Project ID | Project Title | Quarter | Start Date | End Date | Budget (USD) | Status | Milestone 1 | Milestone 2
Q1: January 2024 - March 2024
EDU-001 | Curriculum Development Framework | Q1 2024 | Jan 1, 2024 | Mar 31, 2024 | $85,000 | In Progress | Finalize draft curriculum (Feb 15) | Review by faculty committee (Mar 15)
EDU-002 | Digital Learning Platform Upgrade | Q1 2024 | Jan 10, 2024 | Mar 31, 2024 | $150,000 | In Progress | System assessment complete (Jan 31) | Core features implemented (Mar 1)
Q2: April 2024 - June 2024
EDU-003 | Teacher Training Program Launch | Q2 2024 | Apr 1, 2024 | Jun 30, 2024 | $65,000 | In Progress | Develop training modules (Apr 30) | First cohort trained (May 15)
Q3: July 2024 - September 2024
EDU-004 | Student Assessment System Integration | Q3 2024 | Jul 1, 2024 | Sep 30, 2024 | $110,000 | In Progress | Data mapping completed (Jul 31) | System testing phase (Sep 15)
Q4: October 2024 - December 2024
EDU-005 | Annual Education Review & Reporting | Q4 2024 | Oct 1, 2024 | Dec 31, 2024 | $55,000 | Delayed | Baseline data collection (Oct 31) | Final report submission (Dec 15)
Note:This is a quarterly project plan template for education planning purposes. Status indicators are based on current progress and may be updated quarterly.