## Worksheet
Education Planning - Project Plan Report
Project Name:Advanced Learning Initiative 2024
Department:Academic Development
Status:Active
Start Date:January 15, 2024
End Date:December 31, 2024
Last Updated:October 5, 2023
Phase | Activity/Task | Responsible Party | Start Date | End Date | Status
Planning & Analysis | Needs Assessment Survey Deployment | Dr. Amanda Reed (Lead) | Jan 15, 2024 | Feb 10, 2024 | In Progress
Planning & Analysis | Data Collection and Evaluation Report Drafting | Maria Lopez (Data Analyst) | Feb 11, 2024 | Mar 5, 2024 | Not Started
Curriculum Development | Drafting New Course Frameworks (Grades 9–12) | Prof. James T. Bell (Academic Director) | Mar 6, 2024 | Apr 30, 2024 | In Progress
Curriculum Development | Subject-Matter Expert Review & Feedback Loop | April 1 – May 15, 2024 (Joint Sessions) |  |  | Not Started
Implementation Phase | Teacher Training Workshops (Phase I) | Sarah Kim (Training Coordinator) | Jun 1, 2024 | Jun 30, 2024 | In Progress
Implementation Phase | Classroom Pilot Launch – Grade 9 & 11 (Q3) | Jul 1 – Sep 30, 2024 |  |  | In Progress
Evaluation & Reporting | Mid-Term Performance Review and Adjustments | Dr. Amanda Reed (Lead) | Sep 15, 2024 | Sep 30, 2024 | Not Started
Evaluation & Reporting | Final Project Report and Submission to Board of Education | Nov 1 – Dec 15, 2024 |  |  | Not Started
Report generated on: October 5, 2023 ¦ Version: Report Version v1.0
This document is confidential and intended for internal use only.