## Worksheet
Task | Responsible | Start Date | End Date | Status | Notes
Define Project Goals | Project Manager | 2024-01-05 | 2024-01-10 | Completed | Goals aligned with institutional objectives.
Identify Stakeholders | Coordinator | 2024-01-11 | 2024-01-15 | In Progress | Engaging department heads and faculty.
Develop Curriculum Outline | Curriculum Team | 2024-01-16 | 2024-01-30 | Not Started | Draft based on learning outcomes.
Secure Funding Approval | Finance Officer | 2024-01-20 | 2024-01-31 | Not Started | Pending budget submission.
Hire Teaching Staff | HR Department | 2024-02-01 | 2024-02-15 | Not Started | Recruitment process underway.
Launch Pilot Program | Project Manager | 2024-02-16 | 2024-03-31 | Not Started | Initial rollout to select students.
Evaluate Program Outcomes | Assessment Team | 2024-04-01 | 2024-04-30 | Not Started | Collect feedback and performance data.
Finalize Project Report | Project Manager | 2024-05-01 | 2024-05-15 | Not Started | Summarize results and recommendations.