## Worksheet
Education Planning - Project Plan (Small Business)
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
TASK-001 | Define project goals and objectives | Jane Smith | 2024-04-01 | 2024-04-05 | In Progress | $1,500.00
TASK-002 | Identify target student demographic | Mike Johnson | 2024-04-06 | 2024-04-15 | To Do | $850.00
TASK-003 | Develop curriculum framework | Lisa Brown | 2024-04-16 | 2024-05-10 | To Do | $3,200.00
TASK-004 | Hire qualified instructors | Robert Davis | 2024-05-11 | 2024-06-15 | To Do | $8,500.00
TASK-005 | Secure learning materials and tools | Sarah Wilson | 2024-06-16 | 2024-07-15 | To Do | $3,800.00
TASK-006 | Launch pilot program (limited enrollment) | James Taylor | 2024-07-16 | 2024-09-30 | To Do | $15,000.00
TASK-007 | Collect feedback and evaluate program performance | Emily Clark | 2024-10-01 | 2024-10-31 | To Do | $2,500.00
TASK-008 | Finalize improvements and scale program | Jane Smith | 2024-11-01 | 2024-12-31 | To Do | $7,500.00
Total Estimated Budget | [5 empty] | $42,850.00
Education Planning - Project Plan (Small Business) ¦ Created on April 1, 2024 ¦ Version 1.0