## Worksheet
Task | Start Date | End Date | Status | Responsible | Priority
Define Learning Objectives | 2024-01-05 | 2024-01-15 | In Progress | Jane Smith | High
Develop Curriculum Outline | 2024-01-16 | 2024-01-30 | To Do | John Doe | High
Identify Learning Materials | 2024-01-31 | 2024-02-10 | To Do | Alice Johnson | Medium
Finalize Course Schedule | 2024-02-11 | 2024-02-15 | To Do | Robert Brown | High
Review and Approve Plan | 2024-02-16 | 2024-02-18 | To Do | Sarah Wilson | High
Begin Implementation Phase | 2024-02-19 | 2024-03-15 | To Do | Jane Smith | High