## Worksheet
Education Planning - Project Plan Template
Purpose:Education Planning
Template Type:Project Plan
Style/Version:Template Version 1.0
Task ID | Task Name | Responsible Person | Timeline |  |  | Status | Priority
|  |  | Start Date | End Date | Duration (Days)
T001 | Needs Assessment | Dr. Jane Smith | 2024-04-01 | 2024-04-15 | 15 | In Progress | High
T002 | Curriculum Development | Prof. John Doe | 2024-04-16 | 2024-06-30 | 76 | To Do | High
T003 | Instructor Training | Sarah Johnson | 2024-07-01 | 2024-07-15 | 15 | To Do | Medium
T004 | Resource Procurement | Maria Lopez2024-07-162024-08-1531 Status: Pending Pending | Medium
T005 | Student Enrollment & Onboarding | Derek Brown2024-08-162024-08-3116 Status: Pending Pending | High
T006 | Program Launch & Evaluation | Linda White2024-09-012024-11-3091 Status: Not Started Not Started | High