## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Status
T001 | Define Project Scope | Project Manager | 2023-10-01 | 2023-10-05 | In Progress
T002 | Identify Stakeholders | Coordinator | 2023-10-06 | 2023-10-10 | To Do
T003 | Develop Curriculum Outline | Curriculum Lead | 2023-10-11 | 2023-10-20 | To Do
T004 | Resource Allocation Planning | Resource Manager | 2023-10-15 | 2023-10-25 | In Progress
T005 | Initial Budget Approval | Finance Officer | 2023-10-18 | 2023-10-28 | In Progress
T006 | Finalize Project Timeline | Project Manager | 2023-11-01 | 2023-11-05 | To Do
T007 | Project Kickoff Meeting | Project Manager | 2023-11-06 | 2023-11-06 | To Do