## Worksheet
Education Planning - Project Template (Extended)
Task ID | Task Name | Description | Responsible Person | Start Date | Due Date | Status | Budget (USD)
EP-001 | Needs Assessment Survey | Conduct survey to evaluate current educational gaps. | Jane Doe | 2024-04-15 | 2024-04-30 | In Progress
EP-002 | Curriculum Development Phase 1 | Create core modules for foundational courses. | Mark Smith | 2024-05-01 | 2024-06-15 | Planned
EP-003 | Instructor Recruitment & Training | Hire and train qualified teaching staff. | Sarah Johnson | 2024-05-15 | 2024-07-15 | Planned
EP-004 | Learner Enrollment Campaign | Launch outreach and registration campaign. | Tom Wilson | 2024-06-15 | 2024-08-31 | To Do
EP-005 | Infrastructure Setup & Tech Integration | Install learning platforms and classroom equipment. | Lisa Brown | 2024-07-15 | 2024-10-31 | To Do
EP-006 | Pilot Program Launch (Phase 1) | Run a small-scale trial with selected students. | Alex Rivera | 2024-11-01 | 2025-01-31 | To Do
EP-007 | Evaluation & Feedback Collection | Gather feedback from participants and stakeholders. | Jessica Lee | 2025-02-15 | 2025-03-31 | To Do
EP-008 | Full Rollout Planning & Execution | Scale up based on pilot results and full deployment. | Daniel Kim | 2025-04-15 | 2026-12-31 | To Do