## Worksheet
Education Planning - Project Template (One Page)
Project Phase | Key Activities | Responsible Party | Timeline | Status
Phase 1: Needs Assessment | Evaluate current education gaps, stakeholder requirements, and learning objectives. | Education Coordinator | Week 1–2 | Pending
Phase 2: Curriculum Design | Develop learning modules, set standards, and define assessment criteria. | Curriculum Team | Week 3–5 | Pending
Phase 3: Resource Planning | Identify personnel, budget, materials, and technology needs. | Project Manager | Week 6–7 | Pending
Phase 4: Pilot Implementation | Launch trial program with selected participants and collect feedback. | Instructional Designers & Trainers | Week 8–10 | Pending
Phase 5: Evaluation & Refinement | Analyze results, refine curriculum, and update resources. | Assessment Team | Week 11–12 | Pending
Phase 6: Full Rollout | Implement project across target institutions or regions. | Project Implementation Team | Week 13–16 | Pending
Phase 7: Monitoring & Reporting | Track progress, measure outcomes, and deliver periodic reports. | Monitoring Officer | Ongoing (Week 17–24) | Pending
Total Project Duration: |  |  | 24 Weeks
Note:This one-page project template supports education planning with clear phases, responsibilities, timelines, and status tracking. Customize as needed for your specific context.