## Worksheet
Education Planning - Project Template - Planning View
Phase | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
1. Planning Phase
Planning | Define Project Objectives and Scope | Project Manager | 2024-06-01 | 2024-06-15 | In Progress | $1,500.00
Planning | Identify Stakeholders and Requirements | Lead Educator | 2024-06-16 | 2024-06-30 | Pending | $1,800.00
2. Development Phase
Development | Curriculum Design and Review | Curriculum Specialist | 2024-07-01 | 2024-08-15 | Pending | $8,500.00
Development | Create Learning Materials and Resources | Instructional Designer | 2024-07-15 | 2024-09-30 | Pending | $6,750.00
3. Implementation Phase
Implementation | Teacher Training Sessions | Training Coordinator | 2024-10-01 | 2024-10-31 | Pending | $5,200.00
Implementation | Launch Pilot Program (Grade 9) | Project Manager | 2024-11-01 | 2025-03-31 | Pending | $4,800.00
4. Evaluation Phase
Evaluation | Collect Feedback from Students and Teachers | Educational Analyst | 2025-04-01 | 2025-04-30 | Pending | $3,150.00
Evaluation | Performance Assessment and Reporting | Data Analyst | 2025-05-01 | 2025-06-15 | Pending | $3,450.00
5. Finalization Phase
Finalization | Document Lessons Learned and Best Practices | Project Manager | 2025-06-16 | 2025-07-15 | Pending | $1,980.00
Total Project Budget: | [5 empty] | $37,130.00
Note:This table represents a sample project plan for education planning. All dates and budget figures are illustrative and subject to change based on actual project conditions.