## Worksheet
Education Planning Project Template
Template Type:Project Template
Purpose:Education Planning
Style/Version:Printable
Project Phase | Description | Key Activities | Responsible Person(s) | Status | Dates (Start - End)
Needs Assessment | Evaluate educational needs of target population. | Conduct surveys, stakeholder interviews, curriculum analysis. | Project Coordinator, Educational Analyst | To Do | 2024-01-01 - 2024-01-15
Goal Setting | Define clear and measurable educational objectives. | Establish SMART goals, align with institutional mission. | Program Director, Faculty Lead | In Progress | 2024-01-16 - 2024-01-31
Curriculum Development | Create structured learning modules and materials. | Design lesson plans, develop teaching resources. | Instructional Designer, Subject Matter Experts | To Do | 2024-02-01 - 2024-03-15
Resource Allocation | Identify and assign required materials and funding. | Procure textbooks, technology, training funds. | Fiscal Officer, Logistics Manager | To Do | 2024-01-30 - 2024-02-15
Implementation Phase | Launch and manage the education program. | Deliver classes, monitor student progress, conduct workshops. | Teachers, Mentors, Program Staff | To Do | 2024-03-16 - 2024-12-31
Evaluation & Feedback | Assess program outcomes and gather stakeholder input. | Administer assessments, collect feedback forms, analyze results. | Evaluation Team, Quality Assurance Officer | To Do | 2024-11-01 - 2024-12-31
Reporting & Documentation | Compile final reports and lessons learned. | Create summary report, archive materials, share findings. | Project Coordinator, Documentation Specialist | To Do | 2025-01-01 - 2025-01-31