## Worksheet
Task ID | Task Name | Responsible Person | Start Date | End Date | Status | Description
T001 | Needs Assessment | Project Manager | 2024-01-05 | 2024-01-15 | To Do | Evaluate educational requirements and goals.
T002 | Curriculum Development | Instructional Designer | 2024-01-16 | 2024-03-15 | In Progress | Create course content and learning materials.
T003 | Resource Allocation | Finance Officer | 2024-01-18 | 2024-01-31 | In Progress | Secure budget and physical resources.
T004 | Stakeholder Engagement | Community Liaison | 2024-02-01 | 2024-03-15 | To Do | Hold meetings with parents, teachers, and community leaders.
T005 | Implementation Phase 1 | Lead Instructor | 2024-03-18 | 2024-05-15 | To Do | Pilot the program with selected students.
T006 | Evaluation and Feedback | Program Coordinator | 2024-05-16 | 2024-06-15 | To Do | Gather feedback from participants and make improvements.
T007 | Full Rollout | Project Manager | 2024-06-18 | 2024-12-31 | Closed | Maintain and scale the program across institutions.