## Worksheet
Week | Goal | Activities | Resources Needed | Status
1 | Establish project framework and team roles | Define objectives, assign team members, set communication protocol | Project charter document, team roster, meeting calendar | To Do
2 | Conduct needs assessment and stakeholder analysis | Survey students and educators, identify learning gaps, map stakeholders | Survey tools, interview guide, data analysis software | In Progress
3 | Develop curriculum outline and learning objectives | Create course structure, align with standards, define key outcomes | Curriculum templates, academic standards guide, subject matter experts | In Progress
4 | Design instructional materials and learning modules | Create lesson plans, multimedia content, handouts and assessments | Learning management system (LMS), design software, content templates | To Do
5 | Review and pilot test learning modules with sample group | Run pilot sessions, collect feedback, make revisions based on input | Pilot participant list, feedback forms, revision tracking sheet | To Do
6 | Finalize curriculum and prepare for implementation | Integrate feedback, document final version, schedule rollout plan | Funding approval, implementation timeline, training materials | To Do
7 | Train educators on new curriculum and delivery methods | Conduct training workshops, distribute support guides, provide Q&A sessions | Training agenda, facilitator guide, presentation slides | To Do
8 | Launch project and monitor initial implementation phase | Begin full rollout, track student engagement and progress data | Implementation dashboard, attendance logs, assessment reports | To Do