## Worksheet
Education Planning - Advanced Project Timeline
Phase/Task | Start Date | End Date | Duration (Days) | Status | Progress | Budget Allocation ($)
Phase 1 - Needs Assessment & Planning
Student Needs Analysis | 2024-09-01 | 2024-09-15 | 15 | Ongoing |  | 15,000
Phase 2 - Curriculum Development
Core Course Design | 2024-09-16 | 2024-10-31 | 46 | Ongoing |  | 45,000
Elective Module Development | 2024-11-01 | 2025-01-31 | 92 | Delayed |  | 60,000
Phase 3 - Faculty Training & Onboarding
Training Program Design | 2025-02-01 | 2025-03-15 | 45 | Completed |  | 35,000
Phase 4 - Technology & Infrastructure Setup
LMS Configuration | 2025-03-16 | 2025-04-30 | 46 | Completed |  | 50,000
Phase 5 - Pilot Program Launch
First Cohort Rollout | 2025-05-01 | 2025-10-31 | 184 | Delayed |  | 120,000
Total | [5 empty] | 325,000